## Nodes
Stage | Stage Name | Step ID | Step name | Purpose (Brief one liner to outline purpose of the task) | Description | Automatable | Automation_step
Stage 0 | Declaration of Intent | S1 | Raise Jira Ticket on DP Demand Board | Create a single source of truth to log the demand and kick-off triage. | Step 1: Check for existing/duplicate tickets using keywords and stakeholdersâ€™ names. Step 2: Select the correct Demand Board project and issue type (e.g., Demand/Initiative). Step 3: Enter a clear Summary using the pattern: <Product/Change> â€“ <Outcome> â€“ <Domain>. Step 4: Fill Description with problem statement, desired business outcomes, scope in/out, key risks, and high-level timeline. Step 5: Populate custom fields: domain, sponsoring area, product owner, tech lead, data owner, target environment(s). Step 6: Add labels/tags (e.g., data-product, privacy, security, customer-impact) for filtering and dashboards. Step 7: Link related tickets (defects, dependencies, epics) and any portfolio initiatives. Step 8: Attach supporting artefacts (early notes, diagrams) and grant appropriate permissions/watchers. Step 9: Save and capture the Jira key; share the link with stakeholders. Step 10: Set the status to 'Intake' (or equivalent) to trigger triage workflow and notifications. | FALSE
Stage 0 | Declaration of Intent | S2 | Complete Declaration of Intent (DOI) Form | Document the early concept, value case, and data needs in a standard format. | Step 1: Download/open the latest DOI template and confirm version from the governance space. Step 2: Check Data-Product Naming Standard, each specific for ODP,FCP,CDP. Step 3: Store the signed-off DOI in the repository and link it back to Jira. | TRUE | validate_name
Stage 0 | Declaration of Intent | S3 | Present to Data Products Working Group (DPWG) | Obtain early peer review on feasibility, reuse, and standards alignment. | Step 1: Book a DPWG slot and share pre-read (DOI + 6â€“8 slide deck) 48 hours in advance. Step 2: Prepare deck covering: problem, value, scope, data domains, privacy/security flags, reuse, delivery plan. Step 3: Include a simple scorecard (complexity, risk, reuse potential) to focus discussion. Step 4: Present the proposal (10 minutes) and walk through decisions needed from the group. Step 5: Capture questions, actions, and decisions live in the meeting notes. Step 6: Update the DOI and Jira with outcomes (proceed/refine/park) and named owners for actions. Step 7: Share the updated artefacts and confirm next forum/date (e.g., DPC/ARC). | FALSE
Stage 0 | Declaration of Intent | S4 | Present to Data Products Chapter (DPC) | Secure chapter alignment on ownership, capacity, and ways of working. | Step 1: Book DPC agenda time; circulate DPWG outcome and updated DOI. Step 2: Confirm product ownership and core roles; propose RACI. Step 3: Review capacity and tentative sprint plan; identify staffing gaps. Step 4: Align on tooling, environments, and definition of ready/done for increments. Step 5: Validate dependencies across squads/chapters and agree integration points. Step 6: Record chapter endorsement, conditions, and date to re-confirm if anything changes. Step 7: Update Jira and the catalogue entry with ownership and delivery cadence. | FALSE
Stage 0 | Declaration of Intent | S5 | Endorsement by Data Architecture Review Committee (Data ARC) | Gain architectural endorsement against enterprise and data standards. | Step 1: Prepare an architecture overview (context, C4/system diagrams, data flows, integrations). Step 2: Map to reference architectures and platform standards; call out reuse and deviations. Step 3: Summarise non-functional requirements and how they are met (availability, resilience, performance). Step 4: Highlight security, privacy, data quality, and lineage controls embedded in the design. Step 5: Attend a pre-ARC clinic to test the narrative and capture pre-work actions. Step 6: Present at ARC; seek endorsement with conditions and record actions/owners/dates. Step 7: Update the solution pack and Jira with outcomes; track closure of any conditions. | FALSE
Stage 0 | Declaration of Intent | S6 | Data Product Catalogue Metadata | Register the concept so it is discoverable and governed from day one. | Step 1: Open the catalogue and create a new product entry linked to the Jira key. Step 2: Populate mandatory fields: name, description, domain, owners (product/data/tech), and contacts. Step 3: Add classifications, intended consumers, SLAs/SLOs, and expected availability. Step 4: Register initial datasets, interfaces/APIs, and lineage seeds (producers/consumers). Step 5: Record quality metrics and thresholds, retention rules, and recovery objectives. Step 6: Validate against required field rules; fix warnings; submit for publish. Step 7: Share the catalogue link in Jira and with DPWG/DPC; schedule periodic metadata refresh. | FALSE
Stage 1 | Solution Record | S7 | Complete Your Change Kick Off Form & Raise Solution Record | Formally initiate the change and create the master solution record. | Step 1: Open the change portal and select 'New Solution Record'. Step 2: Enter scope, objectives, environments (dev/test/prod), and dependencies. Step 3: Define non-functional requirements and acceptance criteria. Step 4: Document deployment plan, rollback/contingency, and back-out triggers. Step 5: Identify approval forums (security, privacy, service) and attach the DOI/ARC pack. Step 6: Assign owners and due dates for downstream assessments. Step 7: Submit for registration and capture the solution record ID; link to Jira. | FALSE
Stage 1 | Solution Record | S8 | E2E Cloud Control Assurance | Evidence cloud controls and risk compliance for all components. | Step 1: Inventory cloud services (compute, storage, networking, databases, managed services). Step 2: Map components to control domains (identity, encryption, logging, network, backup/DR, change). Step 3: Complete assurance questionnaire and provide evidence (IaC templates, policies, configs). Step 4: Attach vulnerability scans, CIS benchmarks, and key management procedures. Step 5: Record exceptions/deviations with risk treatments and target closure dates. Step 6: Submit to cloud assurance for review and resolve comments. Step 7: Obtain sign-off and store the assurance report in the solution record. | FALSE
Stage 1 | Solution Record | S9 | E2E Customer Impacts (CSOC) | Assess and mitigate any direct or indirect customer impacts. | Step 1: Identify customer-facing journeys, channels, and any potential outages. Step 2: Assess impacts on SLAs, service windows, communications, and vulnerable customer considerations. Step 3: Define mitigations and draft customer/colleague comms (where required). Step 4: Validate monitoring and incident procedures for customer harm detection. Step 5: Submit assessment to the oversight group and track actions to closure. Step 6: Record the final decision and link comms plan in the solution record. | FALSE
Stage 1 | Solution Record | S10 | Records Management | Ensure records classification, retention, and disposition comply with policy. | Step 1: List records created/consumed by the change and map to record classes. Step 2: Determine retention periods, legal holds, and triggers for disposition. Step 3: Specify storage locations, access controls, and metadata capture requirements. Step 4: Update retention schedules and catalogue entries accordingly. Step 5: Evidence compliance (screenshots, policy mappings) and submit for review. Step 6: Record approvals and link artefacts in the solution record. | FALSE
Stage 1 | Solution Record | S11 | E2E Service Provision Impact Assessment (SPIA) | Validate operational readiness and service support impacts. | Step 1: Identify affected services and owning support groups. Step 2: Define monitoring/alerting, logging, and capacity/performance baselines. Step 3: Update runbooks, KBs, and on-call arrangements; confirm OLAs/SLAs. Step 4: Assess operational risks and required tooling or access. Step 5: Obtain acceptance from service owners and store evidence. Step 6: Link SPIA outputs to the change and go-live checklist. | FALSE
Stage 1 | Solution Record | S12 | E2E Solution Design | Document the target end-to-end design for build and testing. | Step 1: Produce architecture and component diagrams with data flows and interfaces. Step 2: Define schemas/contracts, API endpoints, and transformation/lineage mapping. Step 3: Capture non-functional design (availability, resilience, performance, observability). Step 4: Specify security, privacy, and data quality controls embedded in the design. Step 5: Document error handling, recovery, and deployment strategy. Step 6: Baseline the design after peer review and store in the solution record. | FALSE
Stage 1 | Solution Record | S13 | E2E Architecture | Review and approve the architecture against enterprise standards. | Step 1: Compile the architecture pack (diagrams, ADRs, standards mapping, trade-offs). Step 2: Conduct internal review; address gaps and prepare FAQs. Step 3: Present to the architecture board and walk through key decisions. Step 4: Record approval/conditions and assign owners with due dates. Step 5: Update the pack and the solution record; monitor closure of conditions. | FALSE
Stage 1 | Solution Record | S14 | Service Introduction | Confirm supportability and handover into live operations. | Step 1: Complete the service introduction checklist and identify gaps. Step 2: Finalise support model, RACI, and escalation paths. Step 3: Publish runbooks, KB articles, and training materials for support teams. Step 4: Validate backup/restore, DR plans, and complete a DR test where required. Step 5: Confirm monitoring dashboards and alert thresholds are in place. Step 6: Obtain service acceptance and attach evidence to the solution record. | FALSE
Stage 1 | Solution Record | S15 | E2E Data Privacy (DPIA) | Assess personal-data processing and record privacy risk treatment. | Step 1: Complete DPIA screening to confirm if a full DPIA is required. Step 2: If required, document processing purposes, data categories, lawful basis, and data flows. Step 3: Assess data minimisation, retention, transparency, and data subject rights enablement. Step 4: Evaluate transfers (third parties/locations) and protective measures (e.g., pseudonymisation). Step 5: Identify risks and agree mitigations; record residual risk and owners. Step 6: Obtain privacy approval and store outputs in the solution record. | FALSE
Stage 1 | Solution Record | S16 | E2E Information Security | Confirm security requirements and control effectiveness. | Step 1: Perform threat/risk assessment and define control requirements. Step 2: Evidence identity, access, key/secret management, and encryption controls. Step 3: Provide secure SDLC artefacts (code scan, dependency checks, SAST/DAST results). Step 4: Attach pen-test or security review outcomes and remediation plans. Step 5: Record residual risks and obtain security approval. | FALSE
Stage 1 | Solution Record | S17 | Colleague Impacts (PSOC) | Understand and plan for impacts to colleagues and internal users. | Step 1: Run a change impact assessment across affected roles and processes. Step 2: Define training needs, SOP updates, and access/tooling changes. Step 3: Draft internal communications and adoption plan with milestones. Step 4: Validate business readiness criteria and measures of success. Step 5: Obtain oversight acknowledgement/approval and store evidence. | FALSE
Stage 1 | Solution Record | S18 | Financial Crime | Evidence compliance with AML/sanctions requirements for the change. | Step 1: Confirm whether new or changed data/processes affect screening/monitoring. Step 2: Validate KYC/KYB data availability and data quality for controls. Step 3: Assess transaction monitoring, sanctions screening, and reporting implications. Step 4: Agree control coverage/tuning changes and document testing needs. Step 5: Obtain Financial Crime sign-off and archive evidence in the solution record. | FALSE
Stage 1 | Solution Record | S19 | CMA (Competition and Markets Authority) | Confirm the change aligns with applicable CMA obligations. | Step 1: Identify potential impacts on fair outcomes, disclosures, and competition. Step 2: Review relevant obligations (e.g., pricing transparency, switching) where applicable. Step 3: Obtain legal/regulatory input on any edge cases or mitigations. Step 4: Document the assessment, decisions, and any required controls. Step 5: File the record in the solution repository and link to Jira. | FALSE
Stage 1 | Solution Record | S20 | E2E Group Model Impacts | Identify and govern any model changes or dependencies. | Step 1: Inventory affected models and their purposes/owners. Step 2: Define input data changes, retraining needs, and validation approach. Step 3: Register material changes with model governance and update documentation. Step 4: Plan monitoring (stability, drift, performance) and alerting. Step 5: Obtain required approvals prior to deployment and store evidence. | FALSE
Stage 1 | Solution Record | S21 | E2E Change Gateway | Aggregate evidence for a go/no-go decision across governance areas. | Step 1: Compile approvals from architecture, security, privacy, service, finance, and impact forums. Step 2: Complete the readiness checklist (testing, monitoring, rollback, comms). Step 3: Document risk acceptances and open actions with owners/dates. Step 4: Present to the gateway forum; capture go/no-go decision and conditions. Step 5: Publish decision notes and update the project schedule accordingly. | FALSE
Stage 1 | Solution Record | S22 | E2E Financial Reporting | Validate impacts to finance processes, GL, and regulatory reporting. | Step 1: Map data flows to finance systems and identify GL/reconciliation touchpoints. Step 2: Confirm accounting treatments and materiality with finance controllers. Step 3: Assess impacts on statutory and regulatory returns and control updates. Step 4: Define testing and evidence required for SOX/ICFR as applicable. Step 5: Obtain finance sign-off and link outputs in the solution record. | FALSE

## Edges
from | to | edge_type | guard_condition | Question/Probe | Transactional vs Analytical
S1 | S2 | Mandatory | if JIRA ticket is raised on DPS&G demand board | Share the Jira ticket link please ?
S2 | S3 | Mandatory | if DOI form is complete and naming check is passed | have you been scheduled for DPWG ?
S3 | S4 | Mandatory | if DP being built is FDP or CDP | are you building an FDP or CDP ?
S3 | S5 | Noting | if DP being built is ODP | are you building an ODP?
S4 | S5 | Mandatory | if DP has been endorsed at DPC | Has your DP been endorsed at DPC ?
S5 | S6 | Mandatory | if DP has been endorsed at DARC and a record has been created on Collibra | Has your DP been endorsed at DARC ? Has your DP been created on Collibra ?
S6 | S7 | Mandatory | if all stage 0 tasks have been completed and stage 0 metadata has been populated in Collibra ? | Have you completed all steps in stage 0 checklist ? Have you populated stage 0 metadata requirements ?
S7 | S8 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S14 | Fast Track | if DP is being built using exiting architecture and you can leverage an umbrella record | Is your DP using a toolkit or existing architecture ?
S7 | S9 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S10 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S11 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S12 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S13 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S14 | Mandatory | if you are building an ODP | Are you building an ODP?
S7 | S15 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S16 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S17 | Mandatory | if your DP is reliant on brand new architecture | Is your DP reliant on brand new architecture?
S7 | S18 | Partially Applicable | if this process is applicable for your DP | is this imapct assessment applicable for your DP?
S7 | S19 | Partially Applicable | if this process is applicable for your DP | is this imapct assessment applicable for your DP?
S7 | S20 | Partially Applicable | if this process is applicable for your DP | is this imapct assessment applicable for your DP?
S7 | S21 | Partially Applicable | if this process is applicable for your DP | is this imapct assessment applicable for your DP?
S7 | S22 | Partially Applicable | if this process is applicable for your DP | is this imapct assessment applicable for your DP?
[S8, S9, S10, S11, S12, S13, S14, S15, S16, S17, S18, S19, S20, S21] | S23 | Mandatory | if all necessary SR steps are completed | have you completed all steps in stage 1 checklist ? Have you populated stage 1 metadata requirements ?
S14 | S24 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S25 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S26 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S27 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S28 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S29 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S30 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S31 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S32 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S33 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S34 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S35 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S36 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S37 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S38 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S39 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S40 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S41 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S42 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S43 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S44 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S45 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S46 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S47 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S48 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S49 | Mandatory | if you are building an ODP | are you buiding an ODP?
S14 | S50 | Mandatory | if you are building an ODP | are you buiding an ODP?
[S24, S25, S26, S27, S28, S29, S30, S31, S32, S33, S34, S35, S36, S37, S38, S39,S40, S41, S42, S43, S44, S45, S46, S47, S48, S49, S50] | S51 | Mandatory | if all necessary SI steps are completed | have you completed all steps in stage 2 checklist ? Have you populated stage 2 metadata requirements ?
S51 | S52 | Mandatory | if DR tests have been successfully completed | have you completed all DR requirements ?
S52 | S53 | Mandatory | if all BAU certifications have been comepleted | have yo certified your DP ?